## Sheet1
Row Labels | Sum of Effort
Aneesha | 33
Chandhra | 24
Naveen | 26
Ramarao | 11
saicharan | 24
Grand Total | 118

## Sprint 23_Plan
S.No | Items | Resource | Effort | Start Date | End Date
| Database design | RamaRao, Ghanshyam | 16
| TDD | RamaRao, Ghanshyam | 4 | 25/07/2016 | 25/07/2016
| Requirement Understanding | RamaRao, Ghanshyam | 8
| Code Setup and Git |  | 2
1 | Login | Ghanshyam |  | 26/07/2016 | 27/07/2016
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 3
| UnitTestCases |  | 1
2 | Forgot password | Ghanshyam |  | 27/07/2016 | 28/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 1
| UnitTestCases |  | 0.5
3 | Forgot password notification email | Ghanshyam |  | 28/07/2016 | 28/07/2016
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
4 | ChangePassword/Reset Password(firstlogin or when Admin reset password) | RamaRao |  | 26/07/2016 | 26/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 1
| UnitTestCases |  | 1.5
5 | Permission Options ex. view , edit, delete etc. | RamaRao |  | 26/07/2016 | 27/07/2016
| Screen Design |  | 4
| Database transactions |  | 3
| Business Logic |  | 2
| UnitTestCases |  | 0.5
6 | Creating Role(s) | Ghanshyam |  | 28/07/2016 | 30/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
7 | Creating Group(s) | Ghanshyam |  | 2016-01-08 | 2016-01-08
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
8 | Role Permissions Mappings | RamaRao |  | 27/07/2016 | 28/7/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
9 | Group Role Mappings | RamaRao |  | 29/07/2016 | 30/07/2016
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 1.5
10 | User Creation(user master) | Ghanshyam |  | 2016-02-08 | 2016-03-08
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 3
| UnitTestCases |  | 1.5
11 | Sending Notification To User (after creation) | Ghanshyam |  | 2016-03-08 | 2016-03-08
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
12 | Assign Roles to User | RamaRao |  | 2016-01-08 | 2016-01-08
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 3
| UnitTestCases |  | 1
13 | SecurityQuestionMaster | Ghanshyam |  | 2016-04-08 | 2016-04-08
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
14 | UserSecurityQuestionAnswer | Ghanshyam |  | 2016-04-08 | 2016-05-08
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
15 | BankMaster | Jitendra |  | 26/07/2016 | 26/08/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
16 | BankSubTypeMaster | Jitendra |  | 26/07/2016 | 27/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
17 | SalesYearMaster | Jitendra |  | 27/07/2016 | 27/07/2016
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
18 | FeeMaster | Jitendra |  | 28/07/2016 | 28/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
19 | Notification Master | ramaRao |  | 2016-02-08 | 2016-03-08
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 3
| UnitTestCases |  | 0.5
20 | APIIntegration | Jitendra |  | 29/07/2016 | 29/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 1
21 | SiteMap Role Access Permissions | ramaRao |  | 2016-03-08 | 2016-04-08
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 1
22 | PhoneTypeMaster | Jitendra |  | 30/07/2016 | 30/07/2016
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 1
23 | ContactPerson Title Master | Jitendra |  | 2016-01-08 | 2016-01-08
| Screen Design |  | 2
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 0.5
24 | Affilication Program | Jitendra |  | 2016-01-08 | 2016-02-08
| Screen Design |  | 3
| Database transactions |  | 2
| Business Logic |  | 2
| UnitTestCases |  | 1
25 | ToolTipMaster | RamaRao
| Screen Design |  | 2 | 2016-04-08 | 2016-05-08
| Database transactions |  | 3
| Business Logic |  | 4
| UnitTestCases |  | 1
| Total |  | 180